## User Stories
| Class | CST-247
| Students | Tyler Wiggins Vrijesh Patel
| Description | Minesweeper Web Application Scrum
| Date | 2021-03-28
User Stories |  | Acceptance Criteria
as a user you should be able to save game |  | User can save game
as a user you should be able to save game and resume |  | user can resume game
as a user you should be able to publish game results over a REST based service. |  | user can publish rest based service

## Product Backlog
| Class | CST-247
| Students | Tyler Wiggins, Vrijesh Patel
| Description | Sprint Product Log
| Date | 2021-03-28
Minesweeper Release Projections
Minesweeper Product Backlog | [5 empty] | Running | Sprint | Release | Release
ID | Title | Description | Acceptance Criteria | Type | Size (Fib) | Total | Completed | Dates | Goals
1 | Registration Form | As a user, I can create a new user account. | When I create an account, I can login to the service. | Requirement | 20 | 20
2 | Login Form | As a user, I want to login to the service. | When I login, my credentials are validated and I am granted access. | Requirement | 11 | 11 |  |  | Release 1: Registration and Login Forms
3 | Minesweeper Game | As a user, I want to play minesweeper. | When I login, I can play minesweeper. | Requirement | 34 | 34 |  |  | Release 2: Minesweeper Gameboard
4 | Ajax | As a user, I want to reload page with out losing any game data | When I reload I don’t lose any data | Requirement |  |  |  |  | Release 3 : Minesweeper Ajax
5 | Save game | As a user, I want to save game and resume playing game | I should be able to save game. | Requirement |  |  |  |  | Release 4": Minesweeper Save game.
Note on A6: Instructions: Update the portion in <> with your product's name.
Note on A9: Instructions: Update the portion in <> with your product's name.
Note on A10: Instructions: Enter the ID of the product backlog item (PBI). The ID usually reflects when it was entered in the system, not the priority. The order of the PBIs indicates the priority. This applies to all cells in this column.
Note on B10: Instructions: Enter the title of the product backlog item. Applies to all cells in this column.
Note on C10: Instructions: Enter the product backlog item description. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on D10: Instructions: Enter the product backlog item acceptance criteria. The user story format is provided for your reference in the first row. Applies to all cells in this column.
Note on E10: Instructions: Select what type of product backlog item this is (Applies to all cells in this column): Requirement: Typically a user story--work that needs to be done to generate functionality for the user. Improvement: Action items from the sprint retrospective. Maintenance: Development work that neesd to be done on the system, but doesn't create new functionality.. Overhead: Non-development work that needs to be done, but doesn't add direct value to the user.
Note on F10: Instructions: Enter the Fibonacci size estimate assigned by the development team. Applies to all cells in this column.
Note on H10: Instructions: Enter the number of the sprint when the PBI was completed (done).Enter whole numbers to match the format of what appears in F6:F15 above. Applies to all cells in this column.
Note on I10: Instructions (optional): Update any cell below to point to the date generated in A4:A14 indicating the projected release date. Note: This may change as velocity changes.
Note on J10: Instructions (optional): Update <> with the actual release goal.

## Sprint 3 Backlog and Burndown
| Class | CST-247
| Developers | Vrijesh Patel, Tyler Wiggins
| Description | Burndown
| Date | 2021-03-28
Minesweeper - Sprints
[6 empty] | Available working hours in the sprint |  |  |  | Days in sprint: | 4.5
[7 empty] | M | Tu | W | Th | F | Total
[6 empty] | Developers | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Review + Retrospective
[6 empty] | Vrijesh Patel | 5 | 2 | 4 | 4 | 2 | 17
[6 empty] | Tyler Wiggins | 4 | 3 | 3 | 3 | 2 | 15
[11 empty] | Total sprint hours: | 32
[11 empty] | Total per day: | 7.1111
[7 empty] | M | Tu | W | Th | F
[5 empty] | Story Points | Responsible | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Planning | <DD> Sprint Review + Retrospective | Done (Y) | Accepted (Y/N)
Feature Burndown - Based on estimated hours remaining |  |  |  |  | 45 | All | 45 | 45 | 45 | 45 | 45
[5 empty] | 3 | All | 3 | 3 | 3 | 3 | 3
ID | Task | Description | Acceptance Criteria | Type
1 | Create Minewseeper Board | As a user, I want to play Minesweeper | When I login, I can play minesweeper. | Requirement
| Finish Game Logic | Build View | View must interact with user. | Required |  |  | 27 | 27 | 27 | 27 | 27
[7 empty] | 27 | 20.25 | 13.5 | 6.75 | 0
[6 empty] | Day: | 1 | 2 | 3 | 4 | 5
Actual Hrs Remaining
Schedule Hrs Remaining
Issues
Team Member
N/A

## Design Report
| Class | CST-247
| Students | Vrijesh Patel, Tyler Wiggins
| Description | Site map and Diagram
Current Diagram |  |  | Class Diagram | Sprint Backlog | Sprint Productlog